## Component Inventory
Component | Category | File Path | Lines | Status | Planned in DESIGN.md | Exports | Notes
schema | bridge | bridge/schema.ts | 83 | DONE | Yes | AgentState, ThresholdState, BlockType, BlockOrigin, MessageRole, VoiceId, VoiceColor, VoicePosition, BlockPosition, BridgeBlock, BridgeMessage, BridgeSignals, BridgeVoice, BridgeState, DEFAULT_BRIDGE_STATE
index | main | src/main/index.ts | 43 | DONE | Yes
bridge-watcher | main | src/main/bridge-watcher.ts | 39 | DONE | Yes | startBridgeWatcher
index | preload | src/preload/index.ts | 8 | DONE | Yes
index | renderer | src/renderer/index.html | 18 | DONE | Yes
index | renderer | src/renderer/index.ts | 21 | DONE | Yes
Field | field | src/renderer/field/Field.ts | 119 | DONE | Yes | Field
Presence | field | src/renderer/field/Presence.ts | 514 | DONE | Yes | UserPresence, AgentPresence, VoicePresence, VoiceLayer
ThresholdLine | field | src/renderer/field/ThresholdLine.ts | 65 | DONE | Yes | ThresholdLine
DiskEngine | field | src/renderer/field/DiskEngine.ts | 143 | DONE | Emergent | DiskEngine
OvalStadium | field | src/renderer/field/OvalStadium.ts | 239 | DONE | Emergent | OvalSlot, OvalStadium
ModulationEngine | field | src/renderer/field/ModulationEngine.ts | 122 | DONE | Emergent | DiskBus, OvalBus, VoiceBus, FieldBus, BusValues, ModulationEngine
BlockManager | blocks | src/renderer/blocks/BlockManager.ts | 81 | DONE | Yes | ManagedBlock, BlockManager
CodeBlock | blocks | src/renderer/blocks/CodeBlock.ts | 80 | DONE | Yes | CodeBlockOptions, CodeBlock
ConversationLayer | conversation | src/renderer/conversation/ConversationLayer.ts | 99 | DONE | Yes | ConversationMessage, ConversationLayer
FieldState | state | src/renderer/state/FieldState.ts | 26 | DONE | Yes | FieldState
SessionState | state | src/renderer/state/SessionState.ts | 48 | DONE | Yes | SessionData, SessionState
spaceman | assets | assets/spaceman.svg | 34 | DONE | Yes
electron.vite.config | config | electron.vite.config.ts | 17 | DONE | Yes
AudioEngine | audio | src/renderer/audio/AudioEngine.ts | 85 | DONE | Emergent | AudioParams, AudioEngine
TOTAL |  |  |  | 20/20 done

## Ceremony States
ThresholdState | Sustain | LFO Rate (Hz) | LFO Depth | Disk Scale | Oval Opacity | Voice Alpha | Visual Description
ground | 0.12 | 0.04 | 0.025 | 0.17 | 0.12 | 0.11 | Dim field, small disk, quiet ambient motion
evaluating | 0.5 | 0.18 | 0.07 | 0.53 | 0.39 | 0.45 | Cool-toned disk at ~50%, evaluation pulse ring
floor_rising | 1 | 0.22 | 0.04 | 1 | 0.75 | 0.9 | Disk scaling toward full, warm arc sweep on rim
voices_appearing | 0.85 | 0.12 | 0.05 | 0.86 | 0.64 | 0.77 | Three holographic figures fade in at field positions
voice_1_active | 0.88 | 0.1 | 0.06 | 0.89 | 0.66 | 0.79 | Voice I (amber/left) speaking, pulsing dot above helmet
voice_2_active | 0.88 | 0.13 | 0.06 | 0.89 | 0.66 | 0.79 | Voice II (silver/center) speaking
voice_3_active | 0.88 | 0.09 | 0.06 | 0.89 | 0.66 | 0.79 | Voice III (gold/right) speaking
elevated | 1 | 0.07 | 0.03 | 1 | 0.75 | 0.9 | Full brightness, all voices present, disk at max scale
returning | 0.25 | 0.06 | 0.03 | 0.29 | 0.21 | 0.23 | Field dimming, disk contracting, voices fading
denied | 0.08 | 0.35 | 0.1 | 0.14 | 0.09 | 0.07 | Brief flash, rapid LFO flicker, disk shrinks to minimum

## Development Phases
Phase | Cycle | Component | Depends On | Est. Effort | Test Strategy | Status
0 | Cleanup | snapshot.py + xlsx | - | 1h | manual run | pending
0 | Cleanup | npm run typecheck | - | 15m | CI gate | pending
1 | Morning | Vitest setup | - | 1h | vitest.config.ts + first test | not_started
1 | Morning | SessionState.ts | FieldState.ts | 2h | test: persist/restore round-trip | not_started
1 | Morning | ThresholdLine.ts | ModulationEngine.ts | 2h | test: line draw/dissolve lifecycle | not_started
1 | Morning | FieldState smoke tests | Vitest setup | 1h | test: update + subscribe | not_started
1 | Morning | ModulationEngine tests | Vitest setup | 1h | test: envelope curve, bus output | not_started
2 | Afternoon | CodeBlock.ts | monaco-editor | 3h | test: create/focus/blur/theme | not_started
2 | Afternoon | BlockManager.ts | CodeBlock.ts | 3h | test: CRUD, position, bridge sync | not_started
2 | Afternoon | Block spawn animation | BlockManager.ts | 2h | visual: bridge write trigger | not_started
3 | Evening | ConversationLayer.ts | Field.ts | 3h | test: render + history pruning | not_started
3 | Evening | Audio layer | ModulationEngine.ts | 3h | test: context lifecycle | not_started
3 | Evening | Camera panning | Field.ts | 2h | test: offset tracking | not_started
4 | Rest | spaceman.svg | - | 2h | visual: load as Image | not_started
4 | Rest | Voice sequencing | VoiceLayer | 2h | test: state machine progression | not_started
4 | Rest | Oval slot wiring | OvalStadium.ts | 1h | test: bridge → slot activation | not_started
4 | Rest | Full ceremony test | all | 2h | integration: ground → elevated → return | not_started